## Sheet1
Yosemite Co.
Project Title: | Digitizing Stefano's Shop |  | Start Date: |  | 2023-09-19 | [11 empty] | Display week: |  |  | 1
Project Manager: | Nawras Khudhur |  | Estimated Completion Date: |  | 2023-11-13
[5 empty] | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11
[5 empty] | 2023-09-18 |  |  |  |  | 2023-09-25 |  |  |  |  | 2023-10-02 |  |  |  |  | 2023-10-09 |  |  |  |  | 2023-10-16 |  |  |  |  | 2023-10-23 |  |  |  |  | 2023-10-30 |  |  |  |  | 2023-11-06 |  |  |  |  | 2023-11-13 |  |  |  |  | 2023-11-20 |  |  |  |  | 2023-11-27
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | 2023-09-18 | 2023-09-19 | 2023-09-20 | 2023-09-21 | 2023-09-22 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-10-02 | 2023-10-03 | 2023-10-04 | 2023-10-05 | 2023-10-06 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 | 2023-10-16 | 2023-10-17 | 2023-10-18 | 2023-10-19 | 2023-10-20 | 2023-10-23 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-27 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-20 | 2023-11-21 | 2023-11-22 | 2023-11-23 | 2023-11-24 | 2023-11-27 | 2023-11-28 | 2023-11-29 | 2023-11-30 | 2023-12-01
[5 empty] | 月 | 火 | 水 | 木 | 金 | 月 | 火 | 水 | 木 | 金 | 月 | 火 | 水 | 木 | 金 | 月 | 火 | 水 | 木 | 金 | 月 | 火 | 水 | 木 | 金 | 月 | 火 | 水 | 木 | 金 | 月 | 火 | 水 | 木 | 金 | 月 | 火 | 水 | 木 | 金 | 月 | 火 | 水 | 木 | 金 | 月 | 火 | 水 | 木 | 金 | 月 | 火 | 水 | 木 | 金
Digitizing Stefano's | bar: 月 to 金
Milestone 1: Storefront
Overall Requirement Capturing | Project Manager | 2023-09-19 | 2023-09-25 | 5
Kickoff Meeting | Project Manager | 2023-09-26 | 2023-09-26 | 1
Build Storefront | Engineering Team | 2023-09-27 | 2023-10-10 | 10
Inventory Data Entry | Vendor Manager | 2023-10-11 | 2023-10-17 | 5
Onboarding and Training Stefano's | Vendor Manager | 2023-10-18 | 2023-10-24 | 5
Project Status Report | Project Manager | 2023-10-25 | 2023-10-25 | 1
Knowledge Documentation | Project Manager | 2023-10-27 | 2023-10-31 | 3
Milestone 2: Social Media Integration
Kickoff Meeting | Project Manager | 2023-10-11 | 2023-10-11 | 1
Build Social Media Integration | Engineering Team | 2023-10-12 | 2023-10-25 | 10
Create and handoff Social Media Channels to Stefano's | Marketing Team | 2023-10-26 | 2023-11-01 | 5
Project Status Report | Project Manager | 2023-11-02 | 2023-11-02 | 1
Knowledge Documentation | Project Manager | 2023-11-03 | 2023-11-07 | 3
Milestone 3: Recommendation Engine Integration
Kickoff Meeting | Project Manager | 2023-10-26 | 2023-10-26 | 1
Build Recommendation Engine Integration | Engineering Team | 2023-10-27 | 2023-11-09 | 10
Custom Sales Report Setup | Vendor Manager | 2023-11-10 | 2023-11-16 | 5
Project Status Report | Project Manager | 2023-11-17 | 2023-11-17 | 1
Knowledge Documentation | Project Manager | 2023-11-20 | 2023-11-22 | 3
Live Launch
Release feature into live app | Engineering Team | 2023-11-22 | 2023-11-22 | 1
Formulas:
Week 1 = [Week 1, row below]
Week 2 = [Week 2, row below]
Week 3 = [Week 3, row below]
Week 4 = [Week 4, row below]
Week 5 = [Week 5, row below]
Week 6 = [Week 6, row below]
Week 7 = [Week 7, row below]
Week 8 = [Week 8, row below]
Week 9 = [Week 9, row below]
Week 10 = [Week 10, row below]
Week 11 = [Week 11, row below]