## Sheet1
Waterfall Gantt Chart Template
Project Title: | Luny Phase 2 |  | Start Date: |  | 2022-06-01
Project Manager: | Walyce Almeida |  | Estimated Completion Date: |  | 2022-08-03
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10
[5 empty] | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F
Targeted Ads | bar: WEEK 9 M to WEEK 10 F
Milestone 1: Ad Placement in App
Research customer | Product Manager | 2022-06-01 | 2022-06-01 | 1 | bar: WEEK 1 W
Map customer journey | Product Manager | 2022-06-02 | 2022-06-02 | 1 | bar: WEEK 1 Tr
Make prototype | UX Designer | 2022-06-03 | 2022-06-06 | 2 | bar: WEEK 1 F to WEEK 2 M
Design appearance | UX Designer | 2022-06-07 | 2022-06-07 | 1 | bar: WEEK 2 T
Design functionality | Lead Engineer | 2022-06-08 | 2022-06-09 | 2 | bar: WEEK 2 W to WEEK 2 Tr
Build/code | Engineer | 2022-06-10 | 2022-06-16 | 5 | bar: WEEK 2 F to WEEK 3 Tr
Test functionality | Engineer | 2022-06-17 | 2022-06-20 | 2 | bar: WEEK 3 F to WEEK 4 M
Release into staging environment | Engineer | 2022-06-21 | 2022-06-21 | 1 | bar: WEEK 4 T
Milestone 2: Keyword Algorithm | bar: WEEK 9 M to WEEK 10 F
Research customer | Product Manager | 2022-06-22 | 2022-06-22 | 1 | bar: WEEK 4 W
Map customer journey | Product Manager | 2022-06-23 | 2022-06-23 | 1 | bar: WEEK 4 Tr
Make prototype | UX Designer | 2022-06-24 | 2022-06-27 | 2 | bar: WEEK 4 F to WEEK 5 M
Design appearance | UX Designer | 2022-06-28 | 2022-06-28 | 1 | bar: WEEK 5 T
Design functionality | Lead Engineer | 2022-06-29 | 2022-06-30 | 2 | bar: WEEK 5 W to WEEK 5 Tr
Build/code | Engineer | 2022-07-01 | 2022-07-07 | 5 | bar: WEEK 5 F to WEEK 6 Tr
Test functionality | Engineer | 2022-07-08 | 2022-07-11 | 2 | bar: WEEK 6 F to WEEK 7 M
Release into staging environment | Engineer | 2022-07-12 | 2022-07-12 | 1 | bar: WEEK 7 T
Milestone 3: Ad Settings in Preferences | bar: WEEK 9 M to WEEK 10 F
Research customer | Product Manager | 2022-07-13 | 2022-07-13 | 1 | bar: WEEK 7 W
Map customer journey | Product Manager | 2022-07-14 | 2022-07-14 | 1 | bar: WEEK 7 Tr
Make prototype | UX Designer | 2022-07-15 | 2022-07-18 | 2 | bar: WEEK 7 F to WEEK 8 M
Design appearance | UX Designer | 2022-07-19 | 2022-07-19 | 1 | bar: WEEK 8 T
Design functionality | Lead Engineer | 2022-07-20 | 2022-07-21 | 2 | bar: WEEK 8 W to WEEK 8 Tr
Build/code | Engineer | 2022-07-22 | 2022-07-28 | 5 | bar: WEEK 8 F to WEEK 9 Tr
Test functionality | Engineer | 2022-07-29 | 2022-08-01 | 2 | bar: WEEK 9 F to WEEK 10 M
Release into staging environment | Engineer | 2022-08-02 | 2022-08-02 | 1 | bar: WEEK 10 T
Live Launch | bar: WEEK 9 M to WEEK 10 F
Release feature into live app | Lead Engineer | 2022-08-03 | 2022-08-03 | 1 | bar: WEEK 10 W