## Sheet1
Waterfall Gantt Chart Template
Project Title: | Tory Fitness Digital Plans |  | Start Date: |  | 2023-04-03
Project Manager: | Walyce Almeida |  | Estimated Completion Date: |  | 2023-06-23
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[5 empty] | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F
Building Muscle Plan | bar: WEEK 9 M to WEEK 15 F
Curate materials | Assistant Trainer | 2023-04-03 | 2023-04-14 | 10 | bar: WEEK 1 M to WEEK 2 F
Edit plan | Project Manager | 2023-04-17 | 2023-04-21 | 5 | bar: WEEK 3 M to WEEK 3 F
Create illustrations | Graphic Designer | 2023-04-17 | 2023-04-21 | 5 | bar: WEEK 3 M to WEEK 3 F
Take, edit photos | Photographer | 2023-04-17 | 2023-04-21 | 5 | bar: WEEK 3 M to WEEK 3 F
Add to website | Web Editor | 2023-04-24 | 2023-04-28 | 5 | bar: WEEK 4 M to WEEK 4 F
Getting Lean Plan | bar: WEEK 9 M to WEEK 15 F
Curate materials | Assistant Trainer | 2023-05-01 | 2023-05-12 | 10 | bar: WEEK 5 M to WEEK 6 F
Edit plan | Project Manager | 2023-05-15 | 2023-05-19 | 5 | bar: WEEK 7 M to WEEK 7 F
Create illustrations | Graphic Designer | 2023-05-15 | 2023-05-19 | 5 | bar: WEEK 7 M to WEEK 7 F
Take, edit photos | Photographer | 2023-05-15 | 2023-05-19 | 5 | bar: WEEK 7 M to WEEK 7 F
Add to website | Web Editor | 2023-05-22 | 2023-05-26 | 5 | bar: WEEK 8 M to WEEK 8 F
Toning Up Plan | bar: WEEK 9 M to WEEK 15 F
Curate materials | Assistant Trainer | 2023-05-29 | 2023-06-09 | 10 | bar: WEEK 9 M to WEEK 10 F
Edit plan | Project Manager | 2023-06-12 | 2023-06-16 | 5 | bar: WEEK 11 M to WEEK 11 F
Create illustrations | Graphic Designer | 2023-06-12 | 2023-06-16 | 5 | bar: WEEK 11 M to WEEK 11 F
Take, edit photos | Photographer | 2023-06-12 | 2023-06-16 | 5 | bar: WEEK 11 M to WEEK 11 F
Add to website | Web Editor | 2023-06-19 | 2023-06-23 | 5 | bar: WEEK 12 M to WEEK 12 F

## Sheet 2
Waterfall Gantt Chart Template
Project Title: | Tory Fitness Digital Plans |  | Start Date: |  | 2023-04-03
Project Manager: | Walyce Almeida |  | Estimated Completion Date: |  | 2023-06-23
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[5 empty] | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F
Curate | bar: WEEK 9 M to WEEK 15 F
Plan 1 | Assistant Trainer | 2023-04-03 | 2023-04-14 | 10 | bar: WEEK 1 M to WEEK 2 F
Plan 2 | Assistant Trainer | 2023-04-17 | 2023-04-28 | 10 | bar: WEEK 3 M to WEEK 4 F
Plan 3 | Assistant Trainer | 2023-05-01 | 2023-05-12 | 10 | bar: WEEK 5 M to WEEK 6 F
Edit | bar: WEEK 9 M to WEEK 15 F
Plan 1 | Project Manager | 2023-05-15 | 2023-05-19 | 5 | bar: WEEK 7 M to WEEK 7 F
Plan 2 | Project Manager | 2023-05-22 | 2023-05-26 | 5 | bar: WEEK 8 M to WEEK 8 F
Plan 3 | Project Manager | 2023-05-29 | 2023-06-02 | 5 | bar: WEEK 9 M to WEEK 9 F
Create Illustrations | bar: WEEK 9 M to WEEK 15 F
Plan 1 | Graphic Designer | 2023-05-15 | 2023-05-19 | 5 | bar: WEEK 7 M to WEEK 7 F
Plan 2 | Graphic Designer | 2023-05-22 | 2023-05-26 | 5 | bar: WEEK 8 M to WEEK 8 F
Plan 3 | Graphic Designer | 2023-05-29 | 2023-06-02 | 5 | bar: WEEK 9 M to WEEK 9 F
Photography | bar: WEEK 9 M to WEEK 15 F
Plan 1 | Photographer | 2023-05-15 | 2023-05-19 | 5 | bar: WEEK 7 M to WEEK 7 F
Plan 2 | Photographer | 2023-05-22 | 2023-05-26 | 5 | bar: WEEK 8 M to WEEK 8 F
Plan 3 | Photographer | 2023-05-29 | 2023-06-02 | 5 | bar: WEEK 9 M to WEEK 9 F
Add to Website | bar: WEEK 9 M to WEEK 15 F
Plan 1 | Web Editor | 2023-06-05 | 2023-06-09 | 5 | bar: WEEK 10 M to WEEK 10 F
Plan 2 | Web Editor | 2023-06-12 | 2023-06-16 | 5 | bar: WEEK 11 M to WEEK 11 F
Plan 3 | Web Editor | 2023-06-19 | 2023-06-23 | 5 | bar: WEEK 12 M to WEEK 12 F

## Template
Waterfall Gantt Chart Template
Project Title: | Tory Fitness Digital Plans |  | Start Date: |  | 2023-04-03
Project Manager: | Walyce Almeida |  | Estimated Completion Date: |  | [mm/dd/yy]
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[5 empty] | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F
Phase/Milestone | bar: WEEK 9 M to WEEK 15 F
Task One | Project Manager | 2023-04-03 | 2023-04-14 | 10 | bar: WEEK 1 M to WEEK 2 F
[task] | [assignee] | [dd/mm/yyyy] | [dd/mm/yyyy] | [number of days]
[task] | [assignee] | [dd/mm/yyyy] | [dd/mm/yyyy] | [number of days]
Phase/Milestone | bar: WEEK 9 M to WEEK 15 F
[task] | [assignee] | [dd/mm/yyyy] | [dd/mm/yyyy] | [number of days] | WEEK 1 M: Shade days to match task dates
[task] | [assignee] | [dd/mm/yyyy] | [dd/mm/yyyy] | [number of days]
[task] | [assignee] | [dd/mm/yyyy] | [dd/mm/yyyy] | [number of days]